## Sheet1
Status of NEC ongoing project - Tripura
(Rs. in lakh)
Sl. No. | Sector / Name of Project | Implementing Dept | Executing Agency | Year of sanction | Schedule date of completion as per NEC | Sanctioned cost | NEC Share | State Share | Fund released (Central Share) | Fund released (State Share) | Total Fund Released | Utilisation Certificate submitted (Central Share) | Utilisation Certificate submitted (State Share) | Total UC Submitted (Central+State) | % of expenditure | UC Pending | UC Pending beyond 12 months | Balance NEC share to be released | Balance State share to be released
C1 | C2 | C3 |  | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13 | C14 | C15 | C16 |  | C17 | C18
A | As per list of projects communicated by the Planning Section of NEC vide email dated 9th December, 2020 (Major Head-3601)
1 | Distribution of Crossbreed Pregnant Heifer to the farmers (under Major Head-3601) | ARDD | ARDD | 2013-14 (As per NEC=8/11/2013) | 30th November, 2017 | 360 | 324 | 36 | 259.2 | 28.8 | 288 | 105.3 | 11.7 | 117 | 40.62% | 171 | 194.4 | 64.8 | 7.2
2 | Establishment of State of the Art Sericulture Training Institute, Tripura (under Major Head-3601) | HH & Seri | HH & Seri | 2012-13 (As per NEC=23/11/2012) | 30th November, 2014 | 434.06 | 390.654 | 43.406 | 390.65 | 43.41 | 434.06 | 388.87 | 37.81 | 426.68 | 98.3% | 7.38 | 0 | 0.004 | -0.004
3 | Modernization and Strengthening of Regional Exotic Pig Breeding Farm at Nalkata (under Major Head-3601) | ARDD | ARDD | 2015-16 (As per NEC=20/3/2015) | 31st March, 2016 | 186.55 | 167.895 | 18.655 | 167.9 | 18.65 | 186.55 | 134.3 | 7.46 | 141.76 | 75.99% | 44.79 | 51.11 | -0.005 | 0
4 | Establishment of Rural Collection Centre for Fruits and Vegetables (under Major Head-3601) | Horticulture | Horticulture | 2015-16 (As per NEC=13/5/2015) | 29th February, 2016 | 276.42 | 248.78 | 27.642 | 248.78 | 27.64 | 276.42 | 233.9 | 22.12 | 256.02 | 92.62% | 20.4 | 0 | 0 | 0.002
5 | Strengthening of Exotic Pig breeding farm Birchandra Manu, Tripura (under Major Head-3601) | ARDD | ARDD | 09/03/2016 | 31st March, 2019 | 388.6 | 349.74 | 38.86 | 349.74 | 38.86 | 388.6 | 279.8 | 27.29 | 307.09 | 79.02% | 81.51 | 130.74 | 0 | 0
6 | Setting up of 10 Nos. New Agri Development Research cum Training Centre with IT facilities in Jampuijala, Karbook, Ompi, Killa, Kakraban, Amarpur, Satchand, Jirania, Dukli and Kadamtala, Tripura (under Major Head-3601) | Agriculture |  | 2017-18 (26/2/2018) | February, 2020 | 1295 | 1165.5 | 129.5 | 287 | 0 | 287 | 0 | 0 | 0 |  |  |  | 878.5 | 129.5
7 | Livelihood generation and value addition chain in Piggery Sector based on District Composite Livestock Farm, Nalicherra under Dhalai District, Tripura (under Major Head-3601) | ARDD |  | 15.10.2020 |  | 132 | 118.8 | 13.2 | 62.28 | 6.92 | 69.2 | 0 | 0 | 0 |  | 69.2 |  | 56.52 | 6.28
8 | Construction of 132kV S/C Transmission Line from 132kV Ambassa substation to Gandacherra Substation (47 Ckm)”, Tripura (under Major Head-3601) | TSECL | TSECL | 04.09.2012 | March, 2022 | 1207 | 1086.3 | 120.7 | 900 | 100 | 1000 | 450 | 50 | 500 | 50% | 500 |  | 186.3 | 20.7
9 | Water Arrangement in Rural Areas of Khowai District, West District, Sepahijala District of Tripura/ Sinking & Development of DTW schemes including construction of pump house, installation of pump set laying distribution pipeline etc. (under Major Head-3601) | PWD (DWS) | PWD (DWS) | 2016-17 (02/03/2017) | March, 2019 | 1434.81 | 1291.329 | 143.481 | 1291.33 | 143.48 | 1434.81 | 771.33 | 85.7 | 857.03 | 59.73% | 577.78 | 0 | -0.001 | 0.001
10 | Integrated Development of Incense Cluster at Kumarghat in Tripura (under Major Head-3601) | I&C | I&C | 2013-14 (As per NEC=30/10/2013) | October, 2016 | 779.9 | 701.91 | 77.99 | 701.9 | 78 | 779.9 | 651.9 | 72.44 | 724.34 | 92.88% | 55.56 | 0 | 0 | 0
11 | Revival of Bamboo Sticks Cluster at Kumarghat, Tripura (under Major Head-3601) | I&C | I&C | 2016-17 (28/2/2017) | February, 2020 | 499.29 | 449.361 | 49.929 | 342.74 | 38.08 | 380.82 | 179.74 | 19.97 | 199.71 | 52.44% | 181.11 | 0 | 106.621 | 11.849
12 | Inter-State Truck Terminus at Madhavbari, Jirania (under Major Head-3601) | Transport | PWD (R&B) | 2005-06 (As per NEC=12/09/2005 & 19/01/ 2016) | December, 2018 (Revised) | 2479 | 2231.1 | 247.9 | 2150 | 175.55 | 2325.55 | 1765 | 175.55 | 1940.55 | 83.44% | 385 | 340 | 81.1 | 72.35
13 | Improvement/Upgradation of Bishalgarh-Boxanagar-Sonamura-Barpathari-Belonia Road (under Major Head-3601) | PWD (NH) | PWD (NH) | 2010-11 (As per NEC=29/7/2010) Revised date 23/01/2017 | 5/11/2012 Revised date 31/1/2020 | 23341 | 21006.9 | 2334.1 | 20549.8 | 2266.65 | 22816.45 | 19850 | 1933.32 | 21783.32 | 95.47% | 1033.13 | 699.8 | 457.1 | 67.45
14 | Construction of 50 Type III Residential Quarters for Hostel Superintendent in ST & SC Hostels. (Original cost: Rs. 821.84 lakh, Revised Cost: Rs. 764.88 lakh) (under Major Head-3601) | Secondary Education | PWD (R&B) | 2012-13 (As per NEC=26/3/2013) (Revised sanction date 15.9.2020) | March, 2019 (Revised date 31.3.2021) | 764.88 | 688.392 | 76.488 | 489 | 42 | 531 | 189 | 21 | 210 | 39.55% | 321 | 0 | 199.392 | 34.488
15 | Construction of 100 seated capacity of Men's Hostel at Regional College of Physical Education at Panisagar, North Tripura (under Major Head-3601) | YA & Sports |  | 2017-18 (As per NEC= 16/08/2017). Revised date 13.2.2019. | 31.3.2020 | 468.65 | 421.785 | 46.865 | 274 | 9.34 | 283.34 | 84 | 0 | 84 | 29.65% | 199.34 |  | 147.785 | 37.525
16 | Construction of 200 Bedded (G+2), Yuba Awas (Youth Hostel) in Ambassa, Dhalai District (under Major Head-3601) | YA & Sports | Housing Board | 2016-17 (As per NEC= 16/1/2017) | January, 2019 | 1036.95 | 933.255 | 103.695 | 350 | 38.89 | 388.89 | 280 | 0 | 280 | 72% | 108.89 | 350 | 583.255 | 64.805
| Sub Total: (A. MH-3601) |  |  |  |  | 35084.11 | 31575.701 | 3508.411 | 28814.32 | 3056.27 | 31870.59 | 25363.14 | 2464.36 | 27827.5 | 87.31% | 3756.09 | 1766.05 | 2761.371 | 452.141
B | Other Projects (Not indicated in the list by NEC)
17 | Augmentation of production potential of hybrid true potato seed at Horticulture Research Centre, Nagicherra Tripura (under Major Head-3601) | Horticulture | Horticulture | 2016-17 (28/2/2017) | 28th Februar, 2018 | 181 | 162.9 | 18.1 | 162.9 | 7.2 | 170.1 | 50.8 | 0 | 50.8 | 29.86% | 119.3 | 64.8 | 0 | 10.9
18 | Strengthening of Veterinary Health care services through development of infrastructure (under Major Head-3601) | ARDD | ARDD | 2011-12 (As per NEC=12/10/2011) | October, 2013 | 450 | 405 | 45 | 405 | 45 | 450 | 194.4 | 44.02 | 238.42 | 52.98% | 211.58 | 211 | 0 | 0
19 | Livelihood Generation for returned Migrant Workers due to pandemic outbreak COVID-19 to the state of Tripura (under Major Head-2552). | I&C |  | 23.9.2020 | March, 2021 | 300 | 300 |  | 240 | 0 | 240 | 0 | 0 | 0 |  | 240 |  | 60 | 0
20 | Financial Support to Students of NER for Higher Professional Courses (under Major Head-3601) | Higher Education | Higher Education | 19/11/2004 |  | 2005.65 | 2005.65 | 33 | 2005.65 | 33 | 2038.65 | 1946.66 | 33 | 1979.66 | 97.11% | 58.99 | 0 | 0 | 0
21 | Establishment of India on Track (IOT)- Arsenal Soccer Schools, Youth Development in Tripura through the set up of comprehensive football training and development programme (under Major Head-3601) | YA & Sports | YA & Sports | 2016-17 (As per NEC= 21/03/2017) & 4.2.2019 | March, 2018 | 1500 | 1500 |  | 500 | 0 | 500 | 0 | 0 | 0 | 0% | 500 | 500 | 1000 | 0
22 | Construction of 2X10 MVA 132/33 KV and 2X10 MVA, 33/11 KV Sub-station including LILO at Bisramganj, Sepahijala District, Tripura (under Major Head-3601) | TSECL | TSECL | 2014-15 (As per NEC=28.11.2014) | December, 2018 (Revised) | 1392.24 | 1253.016 | 139.224 | 1253.016 | 139.22 | 1392.236 | 1253.02 | 139.22 | 1392.24 | 100% | -0.004 | 0 | 0 | 0.004
23 | Augmentation by capacity addition of 1X20/25 MVA 132/33 Kv transformer and 2X12.5 MVA, 132/11 Kv transformer with associated equipments at Mission Tilla 132 Kv Sub-station, Dharmanagar, North Tripura (under Major Head-3601) | TSECL | TSECL | 29/2/2016 | December, 2018 | 950.5 | 855.45 | 95.05 | 855.45 | 95.05 | 950.5 | 855.45 | 95.05 | 950.5 | 100% | 0 | 0 | 0 | 0
| B. Sub Total: (Other Projects) |  |  |  |  | 6779.39 | 6482.016 | 677.939 | 5422.016 | 319.47 | 5741.486 | 4300.33 | 311.29 | 4611.62 | 80.32% | 1129.866 | 775.8 | 1060 | 358.469
| Total: (A + B) |  |  |  |  | 41863.5 | 38057.717 | 4186.35 | 34236.336 | 3375.74 | 37612.076 | 29663.47 | 2775.65 | 32439.12 | 86.25% | 4885.956 | 2541.85 | 3821.371 | 810.61